## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story? | branch location
1 | Registered user
1.1 | As a registered user I want to create an acount so that I can have access to every feature on the website | 3 | Noha Amr |  | -
1.2 | As a registered user I want to view/read my acount so that I can review my status. | 3 | Noha Amr | 1.1 | -
1.3 | As a registered user I want to delete my acount | 3 | Noha Amr | 1.1 | -
1.4 | As a registered user I want to update my acount to renew my current status | 3 | Noha Amr | 1.1 | -
1.6 | As a registered user I want to read FAQs section so I can view questions/answers. | 3 | Reem Mohey | - | Noha Amr
1.7 | As a registered user I want to update FAQs section so I can add questions/answers. | 3 | Reem Mohey | - | Noha Amr
1.8 | As a registered user I want to read GUCMUN's About us section. | 1 | Maggie Wagdy | - | Noha Amr
1.9 | As a registered user I want to read AWG's About us section. | 3 | Farida ElShenawy | - | Noha Amr
1.11 | As a registered user I want to read GUCMUN's Events section. | 1 | Sara Walid | - | Noha Amr
1.12 | As a registered user I want to read GUCMUN's Contact us section. | 1 | Hania Hany | - | Noha Amr
1.13 | As a registered user I want to read GUCMUN's Merchandise section. | 1 | Ziad Hesham | - | Noha Amr
1.14 | As a registered user I want to read/view some photos and documents throughout the year with a brief title and description under each one by clicking on "Gallery" so that I can see insights of events that occured throughout the year. | 1 | Seif Darwish | - | Noha Amr | Seif-Darwish
1.15 | As a registered user I want to read GUCMUN's Development section so that I can decide if I should add the club to my interests. | 3 | Ali Aboalam | - | Noha Amr
1.16 | As a registered user I want to read the portal library that includes archives of GUCMUN's conference resolutions and annual academic papers so that I can know more about GUCMUN. | 3 | Rania sedeek | - | Noha Amr
2 | AWG Admin
2.1 | As an AWG Admin I want to create one Admin account so that I can have control over the website. | 3 | Sarah ElFouly |  | -
2.2 | As an AWG Admin I want to update my account so that I can change updated information. | 3 | Sarah ElFouly | 2.1 | -
2.3 | As an AWG Admin I want to view my account to make sure everything is correct. | 3 | Sarah ElFouly | 2.1 | -
2.4 | As an AWG Admin I want to delete my account if we're switching admins. | 3 | Sarah ElFouly | 2.1 | -
2.5 | As an AWG admin I want to create subdomains accounts so that I can manage all subdomains. | 3 | Reem Mohey |  | Sarah ElFouly
2.6 | As an AWG admin I want to update subdomains accounts so that I can update changes in subdomains. | 1 | Reem Mohey | 2.5 | Sarah ElFouly
2.7 | As an AWG admin I want to view/read subdomains accounts so that I can manage all subdomains. | 1 | Reem Mohey | 2.5 | Sarah ElFouly
2.8 | As an AWG admin I want to delete all subdomains accounts so that I can delete any subdomain who wants to quit the website. | 3 | Reem Mohey | 2.5 | Sarah ElFouly
2.9 | As an AWG admin I want to create the FAQs section so that I can offer users help by answering their questions. | 3 | Reem Mohey | - | Sarah ElFouly
2.11 | As an AWG admin I want to update the FAQs section so that I can manage the FAQs section. | 3 | Reem Mohey | 2.9 | Sarah ElFouly
2.12 | As an AWG admin I want to view/read the FAQs section so that I can read the questions. | 1 | Reem Mohey | 2.9 | Sarah ElFouly
2.13 | As an AWG admin I want to delete the FAQs section so that I can delete any inappropriate question/response the FAQs section. | 1 | Reem Mohey | 2.9 | Sarah ElFouly
2.14 | As a AWG admin I want to create about us section so that I can add or edit information about the club, its mission and its goals. | 3 | Farida ElShenawy | - | Sarah ElFouly
2.15 | As a AWG admin I want to delete about us section so that I can delete information about the club. | 3 | Farida ElShenawy | 2.14 | Sarah ElFouly
2.16 | As a AWG admin I want to view/read about us section so that I view the contents of the page. | 3 | Farida ElShenawy | 2.14 | Sarah ElFouly
2.17 | As a AWG admin I want to update about us section so that I can edit information about the club. | 3 | Farida ElShenawy | 2.14 | Sarah ElFouly
3 | GUCMUN Admin | 3 |  |  | -
3.1 | As a GUCMUN admin I want to create Admin Accounts with different and multiple access levels | 3 | Maggie Wagdy | - | -
3.2 | As a GUCMUN admin I want to read/view all Admin Accounts. | 3 | Maggie Wagdy | 3.1 | -
3.3 | As a GUCMUN admin I want to update Admin Accounts so I can change their access levels. | 1 | Maggie Wagdy | 3.1 | -
3.4 | As a GUCMUN admin I want to delete Admin Accounts so I can delete accounts for users who are no longer admins. | 1 | Maggie Wagdy | 3.1 | Maggie Wagdy
3.5 | As a GUCMUN admin I want to create about us section so that I can add or edit information about the club, its mission and its goals. | 3 | Maggie Wagdy | - | Maggie Wagdy
3.6 | As a GUCMUN admin I want to delete about us section so that I can delete information about the club. | 3 | Maggie Wagdy | 3.6 | Maggie Wagdy
3.8 | As a GUCMUN admin I want to view/read about us section so that I view the contents of the page. | 1 | Maggie Wagdy | 3.6 | Maggie Wagdy
3.9 | As a GUCMUN admin I want to update about us section so that I can edit information about the club. | 1 | Maggie Wagdy | 3.6 | Maggie Wagdy
3.1 | As a GUCMUN admin I want to create our events section so that I can post infrmation about people involved in the AWG Hub. | 3 | Sara Walid | - | Maggie Wagdy
3.11 | As a GUCMUN admin I want to read/view information about our events section so that I can check weather they're correct or not. | 3 | Sara Walid | 3.9 | Maggie Wagdy
3.12 | As a GUCMUN admin I want to update our events section so that I can update the infrmation about people involved in the AWG Hub. | 3 | Sara Walid | 3.9 | Maggie Wagdy
3.13 | As a GUCMUN admin I want to delete our events section so that I can delete the infrmation about a certain event. | 3 | Sara Walid | 3.9 | Maggie Wagdy
3.14 | As a GUCMUN admin I want to create a gallery section so that I can add media with optional overlaying text description and captions. | 3 | Seif Darwish | - | Maggie Wagdy | Seif-Darwish
3.15 | As a GUCMUN admin I want to update gallery section so that I can update media with new description. | 3 | Seif Darwish | 3.14 | Maggie Dagdy | Seif-Darwish
3.16 | As a GUCMUN admin I want to delete gallery section so that I can delete media within the gallery. | 3 | Seif Darwish | 3.14 | Maggie Dagdy | Seif-Darwish
3.17 | As a GUCMUN admin I want to view/read gallery section so that I can look at the media in the gallery. | 3 | Seif Darwish | 3.14 | Maggie Dagdy | Seif-Darwish
3.18 | As a GUCMUN admin I want to create GUCMUN development section so that I can add information about the GUCMUN development plan. | 3 | Ali Aboalam | - | Maggie Wagdy
3.19 | As a GUCMUN admin I want to update GUCMUN development section so that I can change information about the GUCMUN development plan. | 3 | Ali Aboalam | 3.18 | Maggie Aagdy
3.2 | As a GUCMUN admin I want to view GUCMUN development section so that I can view information about the GUCMUN development plan. | 3 | Ali Aboalam | 3.18 | Maggie Aagdy
3.21 | As a GUCMUN admin I want to delete GUCMUN development section so that I can delete information about the GUCMUN development plan. | 3 | Ali Aboalam | 3.18 | Maggie Aagdy
3.22 | As a GUCMUN admin I want to create merchandise section so that I can add the merchandise available to the users. | 3 | Ziad Hesham | - | Maggie Hagdy
3.23 | As a GUCMUN admin I want to update merchandise section so that I can change any added information to the section. | 3 | Ziad Hesham | 3.22 | Maggie Hagdy
3.24 | As a GUCMUN admin I want to view/read merchandise section so that I can view the merchandise available to the users. | 3 | Ziad Hesham | 3.22 | Maggie Hagdy
3.25 | As a GUCMUN admin I want to delete merchandise section so that I can delete the merchandise available to the users. | 3 | Ziad Hesham | 3.22 | Maggie Wagdy
3.26 | As a GUCMUN admin I want to create contact us section so that I can add GUCMUN contacts. | 3 | Hania Hany | - | Maggie Wagdy
3.27 | As a GUCMUN admin I want to update contact us section so that I can edit GUCMUN contacts. | 3 | Hania Hany | 3.26 | Maggie Wagdy
3.28 | As a GUCMUN admin I want to read contact us section so that I can view GUCMUN contacts. | 3 | Hania Hany | 3.26 | Maggie Wagdy
3.29 | As a GUCMUN admin I want to delete contact us section so that I can delete GUCMUN contacts. | 3 | Hania Hany | 3.26 | Maggie Wagdy
3.31 | As a GUCMUN admin I want to create a portal library to store academic articles for users to read. | 3 | Rania sedeek | - | Maggie Wagdy
3.32 | As a GUCMUN admin I want to read the portal library to view academic articles available. | 3 | Rania sedeek | 3.31 | Maggie Wagdy
3.33 | As a GUCMUN admin I want to update the portal library to add academic articles for users to read. | 1 | Rania sedeek | 3.31 | Maggie Wagdy
3.34 | As a GUCMUN admin I want to delete the portal library to store academic articles for users to read. | 1 | Rania sedeek | 3.31 | Maggie Wagdy
3.35 | As a GUCMUN admin I want to create my committee's page. | 3 | Farida ElShenawy | - | Maggie Wagdy
3.36 | As a GUCMUN admin I want to update my committee's page. | 3 | Farida ElShenawy | 3.34 | Maggie Wagdy
3.37 | As a GUCMUN admin I want to read my committee's page. | 1 | Farida ElShenawy | 3.34 | Maggie Wagdy
3.38 | As a GUCMUN admin I want to delete my committee's page. | 1 | Farida ElShenawy | 3.34 | Maggie Wagdy