## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | AWG sign up | 3 | Noha Amr | Ziad Hehsam | Hania Hany
1.1 | AWG sign in | 3 | Noha Amr | Ziad Hehsam | Hania Hany
1.2 | AWG homepage | 3 | Hania Hany | Noha Amr | Ziad Hesham
1.3 | AWG FAQs section | 3 | Farida Elshenawy | Reem Mohey | Sara ElFouly
1.4 | AWG account profile | 3 | Farida Elshenawy | Reem Mohey | Sara ElFouly
1.5 | Subdomains page | 3 | Reem Mohey | Farida Elshenawy | Sara ElFouly
1.6 | GUCMUN sign up | 3 | Maggie Serour | Sara Walid | Seif Darwish
1.7 | GUCMUN sign in | 3 | Maggie Serour | Sara Walid | Seif Darwish
1.8 | homepage with a toolbar with multiple sections | 3 | Reem Mohey | Farida Elshenawy | Sara ElFouly
1.9 | events section | 3 | Sara Walid | Maggie Serour | Seif Darwish
2 | gallery section | 3 | Seif Darwish | Maggie Serour | Sara Walid
2.1 | GUCMUN development section | 3 | Ali Aboalam | Noha Amr | Rania Sedeek
2.2 | merchandise section | 3 | Ziad Hesham | Noha Amr | Hania Hany
2.3 | contact us section | 3 | Hania Hany | Noha Amr | Ziad Hesham
2.4 | GUCMUN account profile | 3 | Rania Sedeek | Ali Aboalam | Noha Amr
2.5 | Portal library page with search bar | 3 | Rania Sedeek | Ali Aboalam | Noha Amr
2.6 | Events page with a timeline | 3 | Sara Walid | Maggie Serour | Seif Darwish
2.7 | Gallery page | 3 | Seif Darwish | Maggie Serour | Sara Walid
2.8 | Social media | 3 | Sara ElFouly | Reem Mohey | Farida Elshenawy
2.9 | subscription services | 3 | Sara ElFouly | Reem Mohey | Farida Elshenawy