## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | unregistered/registered user
1.1 | As an unregistered/registered user I want to view/read all the clubs in the university so that I can know more details about the participating AWGs. | 1 | Reem mohey | - | -
1.2 | As an unregistered/registered user I want to be redirected to the club's page which I choose so that I can have an access to the chosen club's page. | 1 | Reem mohey | - | -
1.3 | As an unregistered/registered user I want to view/read the homepage with all of its details so that I can have an access to everything I need. | 1 | Reem mohey | - | -
1.4 | As an unregistered/registered user I want to view/read the descriptions of all participating AWGs so that I can know more details about the participating AWGs. | 1 | Reem mohey | - | -
1.5 | As an unregistered/registered user I want to view/read the announcements posted on the AWG hub so that I can be constantly up to date with the updates happening in any club. | 1 | Sarah ElFouly | - | -
2 | unregistered user
2.1 | As an unregistered user I want to create an account of the AWG Hub so that I can have more access and particapate more in the subdomains. | 8 | Sarah ElFouly | - | -
2.2 | As an unregistered user I want to register online by creating an account using my basic info and peferred councils so that I can have access to every feature of the website. | 8 | Sarah ElFouly | 2.1 | -
3 | Registered user
3.1 | As a registered user I want to access all subdomains so that I can view/read any subdoamin. | 5 | Reem mohey | 2.1, 2.2 | Sarah ElFouly
3.2 | As a registered user I want to log in to any subdomain so that I can be able to view/read, connect and interact with my subdomain. | 5 | Reem mohey | 2.1, 2.2 | Sarah ElFouly
3.3 | As a registered user I want to have an access to my profile so that I can have view, update and delete any information on my profile. | 3 | Reem mohey | 2.1, 2.2 | Sarah ElFouly
3.4 | As a registered user I want to view my information so that I can have access to my information. | 3 | Farida ElShenawy | 2.1, 2.2 | Reem mohey
3.5 | As a registered user I want to update my information so that I can edit my email, password, username, profile picture,etc. | 3 | Farida ElShenawy | 3.4 | Reem mohey
3.6 | As a registered user I want to read, update and delete my questions in the FAQs section. | 3 | Farida ElShenawy | 2.1, 2.2 | Reem mohey
3.8 | As a registered user I want to read mission and vision so that I can have an insight about the goal of the website. | 3 | Farida ElShenawy | 2.1, 2.2 | Reem mohey
3.9 | As a registered user I want to read/view interactive Hierarchy of boards and bodies and by clicking on it i should be sent to another page/section where i can see the full hierarchy so that I can have ease in navigating through the boards. | 3 | Farida ElShenawy | 2.1, 2.2 | Reem mohey
3.1 | As a registered user I want to read/view a slideshow of achievements so that I can view what the website have accomplished. | 3 | Farida ElShenawy | 2.1, 2.2 | Reem mohey
3.11 | As a registered user I want to read/view some photos and documents throughout the year with a brief title and description under each one by clicking on "Gallery" so that I can see insights of events that occured throughout the year. | 3 | Hania Hany | 2.1, 2.2 | Farida ElShenawy
3.12 | As a registered user I want to read/view a brief description about what GUCMUN does and how it influences academic, personal and community development by clicking on “GUCMUN Development” so that I can decide if I should add the club to my interests. | 3 | Hania Hany | 2.1, 2.2 | Farida ElShenawy
3.13 | As a registered user I want to read/view many options of how to contact GUCMUN as leaving a message or icons linked to our social media by clicking on “Contact Us” so that I can contact GUCMUN. | 3 | Hania Hany | 2.1, 2.2 | Farida ElShenawy
3.14 | As a registered user I want to read/view a seperate page for every committe so that I can have exact descriptions of what each committe does, their team members and events if available. | 3 | Hania Hany | 2.1, 2.2 | Farida ElShenawy
3.15 | As a registered user I want to read/view a portal library that includes archives of GUCMUN's conference resolutions and annual academic papers so that I can know more about GUCMUN. | 3 | Hania Hany | 2.1, 2.2 | Farida ElShenawy
3.16 | As a registered user I want to have the ability to create and send anonymous feedbacks by rating the events so that I can provide feedback over the events. | 3 | Noha Amr | 2.1, 2.2 | Hania Hany
3.17 | As a registered user I want to have the ability to create a mailing setvice by Subscribing to mailing services so that I can recieve newsletter and emails from GUCMUN. | 3 | Noha Amr | 2.1, 2.2 | Hania Hany
3.18 | As a registered user I want to read/view a Live Video coverage posted on the website via a notification on the homepage so that I can be aware of what's happening during the event. | 8 | Noha Amr | 2.1, 2.2 | Hania Hany
4 | AWG Admin
4.1 | As an AWG admin I want to read, update and delete all subdomains accounts so that I can manage all subdomains accounts. | 5 | Noha Amr | - | -
4.2 | As an AWG admin I want to create, read, update and delete users so that I can approve accounts to be created, and to delete or edit any suspecious or spam accounts. | 5 | Ziad Hesham | - | -
4.3 | As an AWG admin I want to update and delte the FAQs section so that I can manage the FAQs sectoion. | 5 | Ziad Hesham | - | -
5 | Participating AWG Subdomain
5.1 | As a participating AWG subdomain I want to update AWG hub by posting announcements on so that I can keep users updated with any updates happening in the participating AWGs. | 3 | Ali Aboalam | - | -
6 | GUCMUN Admin
6.1 | As a GUCMUN admin I want to create Admin Accounts with different and multiple access levels | 13 | Maggie Wagdy | - | -
6.2 | As a GUCMUN admin I want to create, update and delete about us section so that I can add or edit information about the club, its mission and its goals. | 5 | Maggie Wagdy | 6.1 | -
6.3 | As a GUCMUN admin I want to create, update and delete our events section so that I can update the infrmation about people involved in the AWG Hub. | 5 | Sara Walid | 6.1 | Maggie Wagdy
6.4 | As a GUCMUN admin I want to create, update and delete gallery section so that I can add media with optional overlaying text description and captions. | 5 | Sara Walid | 6.1 | Maggie Wagdy
6.5 | As a GUCMUN admin I want to create, update and delete GUCMUN development section so that I can update information about the GUCMUN development plan. | 5 | Sara Walid | 6.1 | Maggie Wagdy
6.6 | As a GUCMUN admin I want to create, update and delete merchandise section so that I can add or edit the merchandise available to the users. | 5 | Seif Darwish | 6.1 | Sara Walid
6.7 | As a GUCMUN admin I want to create, update and delete contact us section so that I can update or edit GUCMUN contacts. | 5 | Seif Darwish | 6.1 | Sara Walid
6.8 | As a GUCMUN admin I want to have the ability to limit it to gucians by deleting any other accounts so that I can control whether the users are gucians or not. | 5 | Seif Darwish | 6.1 | Sara Walid
6.9 | As a GUCMUN admin I want to have the ablility to update the field areas to match it with the corresponding event so that I can match those fields to the event's theme. | 5 | Rania Sedeek | 6.1 | Seif Darwish
6.11 | As a GUCMUN admin I want to ability to create, read, update and delete the timeline as pleased so that I can change or update the timelines posted. | 5 | Rania Sedeek | 6.1 | Seif Darwish
6.12 | As a GUCMUN admin I want to create, update, read and delete a timeline that shows and stores all GUCMUN’s main events by years so that I can store GUCMUN main events over the past years and present them to the registered users. | 3 | Rania Sedeek | 6.1 | Seif Darwish
6.13 | As a GUCMUN admin I want to create, update, read and delete a small section that shows our updates on social media whenever we have a new post/update so that I can notify users if there are any updates on social media. | 3 | Rania Sedeek | 6.1 | Seif Darwish
6.14 | As a Secretary office I want to read/access anything on the website so I can help users find their way around the website | 8 | Ali Aboalam | 6.1 | Rania Sedeek
6.15 | As an Executive Office I want to have read/access to only the offices below me so I can implement strategies to support the achievement of the website's strategic and operational objectives | 8 | Ali Aboalam | 6.1 | Rania Sedeek
6.16 | As a USO/ Director/Advocates I want to have control over our office/council page by updating and the ability to assign tasks to someone else so I can Make decisions for the benefit of the website and promote the success of the website | 8 | Ziad Hesham | 6.1 | Ali Aboalam